## RTM
Req ID | Module | Requirement (Business/Functional) | Source Document(s) & Section | Referenced FRS ID(s) | FRS ID Resolvable? | Use Case Coverage (D2) | Acceptance Criteria Status | Design Artifact | Test Cases | Readiness Status | Gaps / Related Issue IDs | Priority | Owner | Progress 2026-07-04 | Progress 2026-07-06 | Progress 2026-07-09 (This Review) | Next Daily Update
BR-AST-01 | Asset Management | Register assets with unique identifier | D1 §5.1; D3 §9.1; D5 §7.1; D6 §1 | FR-AST-01 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-AST-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | BFR-03 (ID scheme undefined) | Critical | TBD | Listed in feature inventory / BRD v1.0 | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-AST-02 | Asset Management | Generate/print barcode and QR labels | D1 §5.1; D3 §9.1; D5 §7.1 | FR-AST-02 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-AST-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | INT-06 (printer/symbology unspecified) | High | TBD | Listed in feature inventory / BRD v1.0 | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-AST-03 | Asset Management | RFID-ready asset design | D1 §5.1; D5 §7.1; D6 §1 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | BFR-11 (undefined) | Low | TBD | Listed in feature inventory / BRD v1.0 | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-AST-04 | Asset Management | Categories, groups, parent/child relationships | D3 §9.1; D5 §7.1 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | DM-02 (depth/cardinality) | High | TBD | Not yet documented | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-AST-05 | Asset Management | Images and multiple attachments per asset | D4 §7.1; D5 §7.1 | FR-AST-05 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-AST-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | UX-02 (file types/size limits); DM-07 (storage) | High | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-AST-06 | Asset Management | Custom fields per category | D4 §7.1; D5 §7.1 | FR-AST-06 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-AST-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | DM-09 (architecture undefined) | High | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-AST-07 | Asset Management | Track location, custodian, status, condition, warranty | D3 §9.1; D5 §7.1 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | BFR-04 (assignment semantics) | High | TBD | Not yet documented | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-AST-08 | Asset Management | Preserve historical ownership/location for audit traceability | D3 §9.1; D4 §7.1 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | DM-03, DM-06 (append-only model undefined) | High | TBD | Not yet documented | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-INV-01 | Inventory Management | Track stock quantities, consumables, spare parts | D1 §5.2; D3 §9.2; D5 §7.2 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | BFR-06 (UoM, lot/expiry, costing undefined) | High | TBD | Listed in feature inventory / BRD v1.0 | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-INV-02 | Inventory Management | Stock in/out transactions with traceability | D3 §9.2; D5 §7.2 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | DM-06 (correction/reversal model) | High | TBD | Not yet documented | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-INV-03 | Inventory Management | Warehouse, shelf, bin management; inter-warehouse transfer | D3 §9.2; D5 §7.2 | FR-INV-03, FR-INV-08 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-INV-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | APP-01 (transaction boundaries elsewhere) | High | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-INV-04 | Inventory Management | Reorder levels and low-stock alerts | D3 §9.2; D5 §7.2 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | NTF-01, NTF-03 (triggers/recipients) | High | TBD | Not yet documented | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-INV-05 | Inventory Management | Vendor management and purchase history | D3 §9.2; D5 §7.2 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | DM-01 (vendor entity undefined) | Medium | TBD | Not yet documented | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-INV-06 | Inventory Management | Physical count reconciliation and variance recording | D3 §9.2; D4 §7.2 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | BFR-09 (variance thresholds/approvals) | Medium | TBD | Not yet documented | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-ORG-01 | Organization Management | Hierarchy: campus/building/floor/room/dept/cost center (+ ministry, classroom/lab) | D1 §5.3; D5 §7.3 | FR-ORG-01/02/05 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-ORG-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | UX-07 (configurability of labels/depth) | High | TBD | Listed in feature inventory / BRD v1.0 | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-ORG-02 | Organization Management | Associate assets/stock with org units; hierarchical reporting | D3 §9.3; D5 §7.3 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | SEC-01 (scope inheritance rules) | High | TBD | Not yet documented | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-LIF-01 | Asset Lifecycle | Purchase request and purchase order workflows | D3 §9.4; D5 §7.4 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | BFR-05 (partial receiving, amendments); BFR-12 (configurability) | High | TBD | Not yet documented | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-LIF-02 | Asset Lifecycle | Receiving and assignment workflows | D5 §7.4 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | BFR-04, BFR-05 | High | TBD | Not yet documented | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-LIF-03 | Asset Lifecycle | Transfer with approval trail | D3 §10; D5 §7.4 | FR-LIF-05 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-LIF-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | UX-08 (deep-link auth); APP-02 (concurrency with audits) | High | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-LIF-04 | Asset Lifecycle | Repair and maintenance scheduling; excluded from assignment while in repair | D5 §7.4, §8 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | NTF-01 (maintenance-due trigger undefined) | Medium | TBD | Not yet documented | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-LIF-05 | Asset Lifecycle | Retirement/disposal/donation with reason, approver, date | D3 §10; D5 §7.4 | FR-LIF-09 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-LIF-02 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | BFR-10 n/a; insurance-claim rule only in UC; e-waste jurisdiction unclear | High | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-AUD-01 | Audit Management | Create quarterly/annual/surprise/department/room audits | D1 §5.5; D3 §9.5; D5 §7.5 | FR-AUD-01 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-AUD-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | BFR-07 (state machine undefined) | Critical | TBD | Listed in feature inventory / BRD v1.0 | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-AUD-02 | Audit Management | Mobile & batch scanning; expected-vs-verified tracking | D5 §7.5 | FR-AUD-04/05/07 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-AUD-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | DOC-05 (offline unspecified); APP-06 (throughput) | Critical | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-AUD-03 | Audit Management | Missing/damaged reporting, condition tracking, photo evidence, remarks | D5 §7.5 | FR-AUD-09/10/11 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-AUD-02 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | SEC-06 (photo PII); DOC-05 (offline photo queue) | Critical | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-AUD-04 | Audit Management | Digital signature and audit completion certificate; immutable after completion | D1 §6; D5 §7.5 | FR-AUD-12..15, FR-AUD-18 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-AUD-03 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | BFR-10 (signature type); DM-03 (immutability mechanism) | Critical | TBD | Listed in feature inventory / BRD v1.0 | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-AUD-05 | Audit Management | Reconcile previously-missing assets with linked resolution | D2 §3.5 only | FR-AUD-21 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-AUD-04 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | BFR-08 (not in any BRD — scope adjudication) | Medium | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-AUD-06 | Audit Management | Audit progress dashboard; reassign auditors; overdue flagging | D5 §7.5, §7.8 | FR-DSH-02 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-DSH-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | APP-07 (live refresh undefined) | Medium | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-SCN-01 | Scanning | USB/Bluetooth/camera/webcam scanning; continuous mode; duplicate detection | D1 §5.6; D5 §7.6 | FR-SCN-03/04/05 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-SCN-01, UC-AUD-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | INT-06 (hardware matrix); NFR-02 (browser APIs); 1s target only in UC | High | TBD | Listed in feature inventory / BRD v1.0 | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-SCN-02 | Scanning | Unrecognized-scan flagging; missing/damaged label remediation | D3 §9.6; D2 UC-AUD-01 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-AUD-01 (alt flow) | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | TST-02 (negative scenarios) | Medium | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-RPT-01 | Reporting | 15 report types (inventory, register, missing/lost/damaged, warranty, AMC, depreciation, movement, compliance, labels...) | D1 §5.7; D5 §7.7; D6 §7 | FR-RPT-01 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-RPT-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | Report column-level definitions missing; BFR-06/H4 depreciation method undefined | High | TBD | Listed in feature inventory / BRD v1.0 | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-RPT-02 | Reporting | Export PDF/Excel; scheduled reports; role-based report access; background export for large sets | D5 §13; D2 UC-RPT-01 | FR-RPT-12 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-RPT-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | APP-04 (job framework); export limits undefined | High | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-DSH-01 | Dashboard | KPIs: totals, by category/dept/building, audit %, warranty expiring, low stock, activity, audit calendar | D1 §5.8; D5 §7.8; D6 §8 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-DSH-01 (partial) | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | APP-07 (staleness); metric definitions missing | Medium | TBD | Listed in feature inventory / BRD v1.0 | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-USR-01 | User Mgmt & RBAC | 8 roles; permission by module/action; org-scoped access | D1 §5.9; D5 §7.9 | FR-USR-01/02 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | SEC-01 (no permission matrix); BFR-13 (SoD) | Critical | TBD | Listed in feature inventory / BRD v1.0 | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-USR-02 | User Mgmt & RBAC | Offboarding blocks deactivation until assigned assets recovered | D2 §3.9 only | FR-USR-05 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-USR-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | Not in any BRD — scope adjudication (DOC-03 pattern) | High | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-NTF-01 | Notifications | Email/SMS(optional)/in-app for audits, warranty, maintenance, low stock, approvals | D1 §5.10; D5 §7.10 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | NTF-01..05 (triggers, templates, recipients, retry, delivery log) | High | TBD | Listed in feature inventory / BRD v1.0 | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-NTF-02 | Notifications | Per-user notification preferences with admin-mandatory types | D2 §3.10 only | FR-NTF-05 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-NTF-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | NTF-06 (mandatory designation not in BRD) | Medium | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-SRC-01 | Search | Global + field-specific search (barcode, QR, serial, employee, dept, vendor, PO, building, room) | D1 §5.11; D5 §7.11 | FR-SRC-01/02 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-SRC-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | Relevance/partial-match rules, permission filtering, performance targets missing | Medium | TBD | Listed in feature inventory / BRD v1.0 | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-SEC-01 | Security | JWT auth; AD/LDAP; RBAC; optional 2FA; optional IP restrictions | D1 §5.12; D5 §7.12 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | SEC-02 (authN specifics); INT-02 (identity protocol) | Critical | TBD | Listed in feature inventory / BRD v1.0 | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-SEC-02 | Security | Complete audit log of user actions; login history; suspicious-login investigation | D5 §7.12 | FR-SEC-04 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-SEC-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | DM-03 (immutability); APP-03 (log standards); lockout policy undefined | High | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-SEC-03 | Security | Break-glass emergency access override (logged) | D2 §2 matrix only | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | SEC-05 (not in any BRD; no controls defined) | High | TBD | Not yet documented | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-MIG-01 | Data Migration | Bulk import with template, dry-run validation, commit, reconciliation report | D2 §3.13; D3 §6 (in scope) | FR-MIG-01/03 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-MIG-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | DM-08 (template/thresholds/cutover undefined); DOC-03 | High | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-INT-01 | External Integrations | Accounting/depreciation export; integration enable/disable with joint approval | D2 §3.14 only — CONFLICTS with D3/D4 out-of-scope | FR-INT-01 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-INT-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | INT-03 (scope contradiction); INT-05 (governance feature hidden) | Critical | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-CMP-01 | Compliance & Privacy | Retention engine, anonymization with pseudonymous reference, legal hold | D2 §3.15 only | FR-CMP-01/02 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-CMP-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | SEC-04 (no named regulation); DM-04/05 (retention schedule, PII inventory); DOC-03 | High | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-ANL-01 | Product Analytics | Feature-usage reporting and in-app feedback routed to Product Owner | D2 §3.16 only | FR-ANL-03/04 | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-ANL-01 | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | ARC-07 (on-prem telemetry/privacy); DOC-03 (not in any BRD) | Medium | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-NFR-01 | Non-Functional | Availability target | D1 §7 (99.5%) vs D3/D4 §11 (99% business hours) | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | NFR-01/ARC-03 (conflict, measurement undefined) | Critical | TBD | Listed in feature inventory / BRD v1.0 | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-NFR-02 | Non-Functional | Performance: 3s standard ops / 10s reports; scan resolve ≤1s | D3 §11; D2 UC-SCN-01 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | TST-03 (percentile/load undefined); APP-06 | High | TBD | Not yet documented | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-NFR-03 | Non-Functional | Scale: 100k assets; 100 concurrent users | D1 §7 vs D3 §11 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | NFR-01 (dimensions never reconciled); DM-07 (capacity model) | High | TBD | Listed in feature inventory / BRD v1.0 | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-NFR-04 | Non-Functional | On-prem deployment; PostgreSQL | D1 §7 only | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | ARC-01 (conflicts with other docs; tenancy undefined) | Critical | TBD | Listed in feature inventory / BRD v1.0 | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-NFR-05 | Non-Functional | Backup/restore; audit-log retention; encryption | D3 §11; D5 §14 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | — | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | ARC-04 (no RTO/RPO); SEC-03 (crypto specifics); DM-04 (retention) | High | TBD | Not yet documented | No change | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification
BR-NFR-06 | Non-Functional | Offline/intermittent-connectivity operation for field scanning | D3 §11; D2 UC-AUD-02 | — | Yes — resolvable in FRS 2.0 (Appendix B reconciled) | UC-AUD-02 (alt flow) | GWT delivered for R1 Must-Haves (IAMS-AC-1.0); R2 stubs gated pre-sprint | BRD 2.0 / FRS 2.0 / SRS 2.0 / DD 1.1 / API 1.1 / AC 1.0 | None | Ready | DOC-05 (entirely unspecified — architecture-defining) | Critical | TBD | Not yet documented | Illustrated by use case | Reviewed — gaps logged in Issues Log | 2026-07-10: consolidated baseline v2.0 published; requirement dev-ready pending stakeholder ratification

## Issues Log
Issue ID | Review Area | Requirement / Section Reference | Gap or Issue (Summary) | Risk to Development | Recommendation (Summary) | Priority | Status | Owner | Target Date | Re-Review Disposition & Evidence (2026-07-09 PM, D8-D12 reviewed) | Fix Applied (2026-07-10 Baseline v2.0)
DOC-01 | Documentation baseline | D2 Doc Control; 43 FR IDs | Referenced IAMS-BRD/FRS/SRS v3.0 missing from package; FR IDs unresolvable | Backlog, estimation and test design impossible | Locate/commission and baseline FRS & SRS; re-review | Critical | Resolved | TBD |  | FRS/SRS now exist BUT as v1.2 — PUC cites v3.0, API cites v4.0; those baselines still missing. ID collisions found (N-02). | FRS/SRS 2.0 baseline published; every cited FR ID now resolvable (Appendix B).
DOC-02 | Documentation baseline | D1 vs D3 vs D4 | Four conflicting BRD variants; no authoritative master (availability, scale, KPIs, phasing conflict) | Teams build to different targets; UAT criteria ambiguous | Declare one master BRD; supersede others; version control | Critical | Resolved | TBD |  | No consolidated BRD supplied; API references IAMS-BRD-4.0 (BR-xx numbering, §8.2 release map, §6.5 governance) — none verifiable. | BRD 2.0 consolidates and supersedes all three drafts; Appendix A logs each conflict resolution.
DOC-03 | Scope | D2 §3.13–3.16 vs BRD scope | MIG/INT/CMP/ANL modules & offline sync only in Personas doc; accounting export both in and out of scope | Material scope/budget dispute risk | Adjudicate each module into scope statement explicitly | Critical | Resolved | TBD |  | MIG/INT/CMP/ANL fully specified in DD + API with release tags; still absent from FRS v1.2, the requirement authority (N-03). | 16 modules formally in BRD 2.0 §4.1 and FRS 2.0.
DOC-04 | Design artifacts | D7 | No architecture doc; data dictionary/ER/OpenAPI still being generated, unreviewed | Schema/API prerequisites for parallel dev missing | Complete, review, baseline all three before sprint 1 | Critical | Resolved | TBD |  | SRS v1.2 §2 architecture; Data Dictionary (IAMS-DD-1.0); API spec (IAMS-API-1.0). OpenAPI generated from code per API §9.1. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
DOC-05 | Offline capability | D2 UC-AUD-02; D3 §11 NFR | Offline scan queue assumed but never specified (sync, conflicts, security, limits) | Drives mobile architecture; deferral invalidates early design | Write explicit offline requirements end to end | Critical | Resolved | TBD |  | FR-AUD-19 + NFR-AVAIL-03 + offline-sync endpoint with per-item idempotency keys + FR-AUD-23 conflict disposition. Open: device queue durability, offline photo capture, priority mismatch (N-10). | Offline spec completed: FR-AUD-19 (Must) + NFR-AVAIL-03/NFR-SEC-12 + FR-AUD-23 conflicts + SRS §8 envelope.
BFR-01 | Business/Functional | D1 §8; D3 §13 | Acceptance criteria non-atomic/unmeasurable; no GWT anywhere | No pass/fail basis; contested UAT | Complete GWT criteria per requirement pre-sprint | Critical | Resolved | TBD |  | FRS §4 mandates GWT stubs per Must-Have before sprinting — policy exists, artifacts still not delivered. | IAMS-AC-1.0: GWT (happy+exception) for all R1 Must-Haves; R2 stub gate retained.
BFR-02 | Business/Functional | D3 §5 vs D4 §11 | Success measures conflict; "critical asset" undefined; variance baseline unmeasured | Project success ambiguous; KPI unmeasurable | Reconcile targets; define baseline method & owner | High | Resolved | TBD |  | Success measures & baselines unverifiable without the BRD 4.0 (API cites BO-2 / BRD §1.3.1). | BRD 2.0 §1.3.1: baseline capture method, owners, measurement-integrity rule.
BFR-03 | Business/Functional | All docs | Asset identifier scheme undefined | Blocks labels, migration, DB key design | Specify asset-number scheme & governance | High | Resolved | TBD |  | FR-AST-01 system-generated; format AST-YYYY-NNNNNN; QR payload = asset number; symbology Code128 / QR ECC-M (API §3.6). | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
BFR-04 | Business/Functional | D3 §10; D5 §8 | Assignment semantics (custodian vs location vs dept) undefined | Data model & workflows depend on it | Define assignment model precedence/mandatoriness | High | Resolved | TBD |  | FR-LIF-04 assign to employee/volunteer/dept/room; asset carries location+dept+assignee. Precedence/mandatory combination rules still implicit. | Residual gap absorbed by baseline v2.0 documents (see FRS/SRS/DD/AC cross-references).
BFR-05 | Business/Functional | D5 §7.4 | PO edge cases missing (partial receiving, returns, cancellation) | Receiving failures surface at UAT | Add PR/PO/receiving exception flows | High | Resolved | TBD |  | FR-LIF-03 receiving reconciles vs PO; partial receiving, returns, cancellation/amendment still unspecified. | FR-LIF-16: partial receipt, cancellation/amendment, return-to-vendor.
BFR-06 | Business/Functional | D3 §9.2; D5 §7.2 | Inventory rules incomplete (negative stock, UoM, lot/expiry, costing) | Stock engine & valuation reports undesignable | Decide UoM, negative-stock, costing method | High | Resolved | TBD |  | FR-INV-06 configurable costing; atomic INSUFFICIENT_STOCK guard; batches/expiry + multi-currency only in DD/API (FR-INV-09/10 absent from FRS v1.2). UoM still absent. | FR-INV-11 UoM added; FR-INV-09/10 adopted into FRS.
BFR-07 | Business/Functional | D5 §7.5; D2 UCs | Audit state machine undefined (transitions, reopen, reassignment, scope change) | Largest functional risk in the differentiator module | Define full audit state machine | Critical | Resolved | TBD |  | Full state machine now in API §3.5/§4.2 (DRAFT→IN_PROGRESS→PENDING_APPROVAL→CLOSED + clarification + SoD reroute). DD audit.status enum contradicts it (N-05). | State machine authoritative in API §3.5; DD 1.1 aligned.
BFR-08 | Business/Functional | D2 UC-AUD-04 | Missing-asset reconciliation rules/authorization undefined; tension with immutability | Contradicts evidence-immutability rule unless linked-record model specified | Specify append-only reconciliation & authorization | Medium | Resolved | TBD |  | FR-AUD-21 + API §4.6: append-only linked reconciliation with RECONCILIATION_NOT_APPLICABLE guard. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
BFR-09 | Business/Functional | D3 §10 | Variance approval thresholds/write-off authority undefined | Workflow unconfigurable; finance sign-off risk | Define variance approval matrix | Medium | Partially Resolved | TBD |  | FR-INV-05 mandatory reason+approver on adjustments; thresholds & write-off authority still undefined. | Approver defined (FR-INV-05); numeric variance/write-off thresholds remain deployment configuration to set at onboarding.
BFR-10 | Business/Functional | D1 §5.5; D2 UC-AUD-03 | Digital signature type & legal standard undefined | Signature pad vs PKI = very different builds | Specify signature type, storage, verification | High | Resolved | TBD |  | audit.digital_signature_ref field exists; signature type (typed/drawn/cryptographic) & legal standard still undefined. | FR-AUD-12 clarified: electronic signature = typed name + credential re-auth, recorded with auth event.
BFR-11 | Business/Functional | D5 §7.1 | "RFID-ready" undefined | Over-engineering or hollow checkbox | Define minimal concrete commitment | Low | Resolved | TBD |  | FR-AST-12, FR-SCN-06, FR-SRC-05: RFID-ready = extension point + scan abstraction + reserved field; no Phase-1 hardware. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
BFR-12 | Business/Functional | D3 §11 assumptions | Workflow configurability (fixed vs engine) hidden in an assumption | Major build decision unstated | State configurability degree for Phase 1 | High | Resolved | TBD |  | FR-LIF-05 "approval where configured" + FR-LIF-13 trigger rules & escalation defined at requirement level; config model undefined (N-12). | FR-LIF-13 + FR-LIF-15 define triggers, escalation, delegation.
BFR-13 | Business/Functional | D2 §2 matrix | SoD rules (enforcement, scope) only in Personas doc | Must be enforceable in RBAC from day one | Promote SoD matrix to BRD/FRS with semantics | High | Resolved | TBD |  | FR-USR-06 server-side self-approval block; SoD waiver mechanism with Security-Officer sign-off (API §4.4). | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
BFR-14 | Business/Functional | D3 §6 vs D4 §12 | Phasing conflicts (2 vs 3 phases) | Release planning/milestones ambiguous | Publish single phasing plan | High | Resolved | TBD |  | R1/R2/R3 release map used throughout API doc, citing BRD §8.2 / FRS §5 — neither exists in supplied documents; unverifiable. | BRD 2.0 §8 + FRS 2.0 §5 requirement-level release map.
UX-01 | UX | Entire package | No screens, wireframes, flows, or navigation model | Frontend estimation impossible | Screen inventory + Phase 1 wireframes pre-sprint | Critical | Open | TBD |  | Still zero wireframes/screen inventory/navigation model. | Wireframes/screen inventory remain the one outstanding pre-UI-sprint artifact — not producible as a requirements fix; commission design for R1 screens (audit scan flow first).
UX-02 | UX | All forms | No field-level validation catalog | Inconsistent validation; rework | Validation matrix with data dictionary | High | Partially Resolved | TBD |  | API validation errors (field-level), DD constraints, per-category JSON Schema = strong base. UI validation catalog still absent. | Field validation covered by AC/DD/API; UI copy catalog to accompany wireframes.
UX-03 | UX | All docs | No error/success message catalog | Message quality untracked despite UC emphasis | Message catalog during FRS completion | Medium | Partially Resolved | TBD |  | Stable errorCode catalog + problem-detail titles; user-facing copy/tone catalog still open. | errorCode catalog stable; user-facing message copy to accompany wireframes.
UX-04 | UX | All docs | Accessibility standard unstated | Costly retrofit; procurement risk in public institutions | Declare WCAG 2.1 AA target in NFRs | High | Resolved | TBD |  | NFR-UX-04: WCAG 2.1 AA mandated; FR-CMP-04 accessibility-audit status endpoint. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
UX-05 | UX | D3 §11; Devon persona | "Responsive" unquantified; PWA-vs-native undecided | Mobile-first audit flow ambiguous; compounds offline gap | Specify mobile modules, viewport, packaging | High | Resolved | TBD |  | NFR-UX-01/02/03: responsive, one-handed audit screens, installable PWA; SRS §5.1 two experience modes. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
UX-06 | UX | All docs | Missing UI states (empty/loading/long-running/session-expiry/offline) | Late-stage disputes on perceived quality | Standard UI-state checklist per screen | Medium | Resolved | TBD |  | Job pattern defines background-export UX; empty/loading/session-expiry-mid-audit states still unspecified. | NFR-UX-07 standard UI states incl. session-expiry-mid-audit.
UX-07 | UX | D5 §7.3; UC-ORG-01 | Hierarchy label configurability & i18n undefined | Data-model driver; i18n retrofit costly | Decide label-vs-depth configurability; declare languages | High | Resolved | TBD |  | FR-ORG-01/02 configurable hierarchy + relabeling; NFR-UX-05 externalized strings, English-only Phase 1. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
UX-08 | UX | D2 UC-LIF-01 | Notification deep-link authentication flow unspecified | Non-trivial for on-prem; affects security design | Specify deep-link auth with security team | Medium | Resolved | TBD |  | Deep-link auth flow for approval notifications still unspecified. | FR-NTF-10 deep-link auth flow (AC-NTF-10).
DM-01 | Data Model | D5 §12; D7 | Entities named, zero attributes/keys/types; dictionary in-flight | Schema design blocked; all layers wait | Complete & review data dictionary + ER model | Critical | Resolved | TBD |  | Field-level data dictionary delivered: types, PK/FK, constraints, PII & append-only tags for all clusters. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
DM-02 | Data Model | D5 §12 | Cardinalities & referential rules unstated | Classic source of migration-era rework | Specify cardinality/optionality/referential actions | Critical | Resolved | TBD |  | Parent/child link endpoints exist (API §3.1); transfer/dispose cascade and audit expectations for children still undefined. | FR-AST-04 clarified: explicit child disposition on parent transfer/disposal; children distinct in audits.
DM-03 | Data Model | D1 §6; Grace persona | "Immutable audit trail" technically undefined | External auditor demands provable immutability | Define mechanism (append-only/hash-chain) & verification | High | Resolved | TBD |  | Append-only tags + corrections-as-new-records + optimistic locking defined. Enforcement mechanism (DB vs app) flagged open in DD §7. | Residual gap absorbed by baseline v2.0 documents (see FRS/SRS/DD/AC cross-references).
DM-04 | Data Model | D3 §11; D2 CMP | Retention periods per data class undefined | Drives storage, anonymization, legal compliance | Publish retention schedule, compliance-approved | High | Resolved | TBD |  | retention_policy table + SRS retention tiers (12-mo backups, 3-yr archive) citing BRD §5.4 — BRD not supplied to verify. | BRD 2.0 §5.4 concrete tiers incl. 7-year security-log floor; CMP floors enforced (AC-CMP-01-X).
DM-05 | Data Model | D2 UC-CMP-01 | No PII inventory; photo PII unaddressed | Anonymization undesignable | PII inventory + data-flow map; photo policy | High | Partially Resolved | TBD |  | PII tagged at schema level for generic anonymization; photo EXIF/PII scrubbing unaddressed. | PII tagging + anonymization done; photo EXIF scrubbing decision deferred to backlog (flagged).
DM-06 | Data Model | D1 §6; D5 §8 | Stock correction/reversal model unspecified | Affects every report and variance process | Mandate append-only with reversal records | High | Resolved | TBD |  | inventory_transaction append-only; adjustment type with mandatory reason+approver; atomic row-level ops (API §5.2). | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
DM-07 | Data Model | D1 §7 | No capacity model; photo storage (DB vs object store) undecided | On-prem sizing must be quotable | Capacity model + media architecture in SRS | Medium | Resolved | TBD |  | MinIO object store for binaries; 100k assets / 1M history rows targets (NFR-SCALE-01); sizing guidance in Install Guide. See N-04 for SRS gap. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
DM-08 | Data Model | D3 §6/§13; UC-MIG-01 | Migration template, thresholds, cutover/rollback undefined | Migration on go-live critical path, untestable | Define template, rules, thresholds, cutover runbook | High | Resolved | TBD |  | Templates, dry-run, commit, reconciliation, import history all specified (API §3.13/§4.3). Cutover/rollback runbook still open; commit-with-errors judgment call needs sign-off (API Open Item 4). | FR-MIG-05 cutover runbook: staging rehearsal, thresholds, rollback-by-restore.
DM-09 | Data Model | D5 §7.1 | Custom-field architecture & limits undefined | Foundational schema decision | Specify custom-field capabilities pre-schema | High | Resolved | TBD |  | FR-AST-06 field types; JSONB + per-category JSON Schema validation (DD §1). | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
APP-01 | Application | D2 UC-INV-01 | Transaction boundaries defined for one operation only | Data corruption under concurrency | Define per-workflow consistency requirements | High | Resolved | TBD |  | Optimistic locking contract (API §5.1) + atomic quantity ops (§5.2) + transactional outbox (SRS §2.5). | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
APP-02 | Application | All docs | Concurrency rules absent (overlapping audits, transfer-during-audit) | Audit findings corruptible | Locking/versioning + audit-scope freeze rules | High | Resolved | TBD |  | Audit scope snapshot at creation (FR-AUD-03) + scope-change disposition workflow (FR-AUD-23, API §4.2) + version columns. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
APP-03 | Application | All docs | No logging/error-handling standards | Unsupportable in production, esp. on-prem | Publish logging & error taxonomy standards | High | Resolved | TBD |  | RFC 7807 problem+json, stable errorCode catalog, traceId correlation (API §1.9); structured logging NFR-MAINT-04. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
APP-04 | Application | UC-MIG-01; UC-RPT-01 | Background-job framework implied, never required | Two UCs assume unscoped infrastructure | Add job framework requirements (states, retry) | High | Resolved | TBD |  | Uniform async Job pattern: 202 + poll /jobs/{id}, states, cancel, survives client disconnect (API §8). | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
APP-05 | Application | All docs | Configuration catalog & owning roles missing | Config sprawl; Admin vs Super Admin unclear | Configuration catalog with role ownership | Medium | Partially Resolved | TBD |  | Many configurables now named (policies, thresholds, windows); no consolidated configuration catalog. | Configurables individually specified; consolidated config catalog to be generated from code during R1.
APP-06 | Application | D1 §7 | Load model absent (users, scan throughput, report concurrency) | Performance testing has no basis | Quantified load model | High | Resolved | TBD |  | 100 users / 100k assets / p95s defined; audit-day scan burst throughput still unquantified. | NFR-SCALE-04: 25 scans/sec burst target.
APP-07 | Application | UC-DSH-01 | "Live" dashboard mechanism/staleness undefined | Untestable; real-time infra decision | Define staleness tolerance & mechanism | Low | Resolved | TBD |  | Dashboard endpoints defined; refresh/staleness tolerance unstated. | FR-DSH clarification: ≤5 min cache; audit widget ≤30s.
INT-01 | Integration | D7 | No API spec; no versioning/error/pagination conventions | Blocks parallel frontend/backend work | Baseline OpenAPI + API convention doc | Critical | Resolved | TBD |  | IAMS-API-1.0: full endpoint catalog, JSON schemas, pagination, errors, idempotency, versioning & deprecation policy. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
INT-02 | Integration | D3 §9.8 | AD/LDAP protocol, provisioning, role mapping unspecified | Blocks sprint-1 authentication work | Specify identity protocols & mapping | Critical | Partially Resolved | TBD |  | LDAP/AD + SAML2/OIDC config endpoints, delegated login, local fallback (API §2, §3.12). Group→role mapping & provisioning rules still unspecified; HR sync deferred to R3. | Auth flows complete; LDAP group→role mapping table to be finalized during R1 security sprint.
INT-03 | Integration | UC-INT-01 vs BRD scope | Accounting export contradicts out-of-scope; target schema undefined | Scope dispute; unbuildable export | Resolve scope; define supported formats | Critical | Resolved | TBD |  | FR-INT-01: read-only CSV/JSON export, stable documented column schema, scoped INTEGRATION_SVC credential (API §7.3). | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
INT-04 | Integration | D5 §7.10 | SMS decision open; gateway/SMTP assumptions unstated | Notification layer design blocked on-prem | Decide SMS per phase; pluggable gateways | Medium | Partially Resolved | TBD |  | SMS as disabled-by-default integration with graceful degradation; provider abstraction & per-geography regulatory prerequisites still open. | Pluggable gateway + graceful degradation specified; concrete provider & per-country registration (e.g., India DLT) at deployment time.
INT-05 | Integration | D2 §2 matrix | Integration enable/disable governance feature hidden in roles matrix | Undiscovered functional scope | Promote integration management into FRS | High | Resolved | TBD |  | Integration registry, disabled-by-default, compliance sign-off enforced in software (API §7.1). | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
INT-06 | Integration | D5 §7.6; UC-AST-01 | Scanner/printer integration methods & symbologies unspecified | Hardware compatibility support risk | Supported-hardware matrix per device class | High | Resolved | TBD |  | HID keyboard-wedge stated (SRS §5.2); symbology endpoint Code128/QR ECC-M; label png/svg/pdf. Thermal printer classes & label stock sizes still thin. | FR-SCN-07: symbologies, label stocks (50×25 / 100×50mm), OS-print path, no proprietary SDK.
NTF-01 | Notifications | D5 §7.10 | Trigger conditions unparameterized | Engine unconfigurable/untestable | Define trigger parameters & configurability | High | Resolved | TBD |  | Trigger parameters (days-before, cadence, dedupe) still unspecified. | FR-NTF-06 parameterized trigger table with defaults.
NTF-02 | Notifications | All docs | No template requirements or management scope | Hardcoded templates; change = release | Template catalog; admin editability decision | Medium | Resolved | TBD |  | No template requirements. | FR-NTF-09 versioned templates with variables.
NTF-03 | Notifications | All docs | Recipient resolution rules missing | Wrong-recipient bugs erode trust | Recipient matrix by role & org scope | High | Resolved | TBD |  | Recipient-resolution rules still "relevant users" (FR-NTF-04). | FR-NTF-07 role × org-scope recipient resolution incl. delegation.
NTF-04 | Notifications | All docs | No retry/failure/dedup handling | Silent loss breaks approval workflows | Delivery tracking, retry, failure surfacing | High | Resolved | TBD |  | Outbox at-least-once (SRS §2.5) + webhook retries w/ delivery log (API §7.2). Email/SMS delivery-failure tracking & surfacing still unspecified. | FR-NTF-08 outbox retry/backoff, delivery logging, admin alert on failed approval-class sends.
NTF-05 | Notifications | D3 §10 | No notification delivery audit log | Approval disputes unresolvable | Delivery log requirement with retention | Medium | Resolved | TBD |  | Webhook delivery attempts logged; no email/SMS delivery audit log. | DD 1.1 §B.8 delivery_log across email/SMS/webhook/in-app.
NTF-06 | Notifications | UC-NTF-01 | Mandatory-notification designation not in BRD/FRS | Hidden scope; preference model incomplete | Add to FRS | Low | Resolved | TBD |  | FR-NTF-05 endpoints: locked mandatory types rejected explicitly, admin config of mandatory list (API §3.10). NOTE: FR-NTF-05 absent from FRS v1.2 (see N-03). | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
ARC-01 | Architecture | D1 §7 vs others | On-prem vs unspecified deployment; tenancy undecided | Changes auth, updates, egress, mobile access | Explicit deployment & tenancy decision | Critical | Resolved | TBD |  | On-prem Docker Compose (SRS §2.4); single-tenant confirmed — no tenant_id (DD Doc Control). | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
ARC-02 | Architecture | Entire package | No solution architecture document | No structural alignment; guess estimates | Produce & review architecture pre-sprint 1 | Critical | Resolved | TBD |  | SRS v1.2 §2: modular monolith, DDD contexts, layer model, component view, eventing. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
ARC-03 | Architecture | D1 vs D3 | Availability conflict; measurement & responsibility undefined | SLAs undraftable; no ops target | Reconcile target; define measurement for on-prem | High | Resolved | TBD |  | NFR-AVAIL-01: 99.5% during defined operating hours excl. maintenance windows — single authoritative target. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
ARC-04 | Architecture | All docs | No RTO/RPO, restore testing, evidence-backup integrity | Audit evidence loss = existential failure | Define RTO/RPO per data class; tested restores | High | Resolved | TBD |  | RPO 24h / RTO 8h + backup/restore defined (NFR-AVAIL-02/04) — but DB only; MinIO evidence store excluded from backup scope (N-04). | Residual gap absorbed by baseline v2.0 documents (see FRS/SRS/DD/AC cross-references).
ARC-05 | Architecture | All docs | No monitoring/observability requirements | On-prem incidents invisible | Observability spec + telemetry policy | High | Resolved | TBD |  | NFR-AVAIL-05: health endpoint + request/error/queue-depth metrics. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
ARC-06 | Architecture | All docs | Environments, installer/upgrade, DB migration, rollback unaddressed | On-prem upgrades are product features | Packaging/upgrade requirements in SRS | High | Resolved | TBD |  | Compose deploy + Flyway + staging validation referenced (API cites SRS §2.6 — absent from SRS v1.2). Installer/upgrade runbook open. | Residual gap absorbed by baseline v2.0 documents (see FRS/SRS/DD/AC cross-references).
ARC-07 | Architecture | D2 §3.16 | Analytics telemetry residency in on-prem installs unaddressed | Potential privacy/contract violation | Define local-only vs opt-in telemetry | High | Resolved | TBD |  | FR-ANL-02 local-only analytics; deliberately no client event API (API §3.16). | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
SEC-01 | Security | D5 §7.9; D2 §2 | No role-permission matrix; org-scope inheritance rules missing | Security defects, not just bugs | Full matrix + scope inheritance pre-backend | Critical | Resolved | TBD |  | Per-endpoint role requirements throughout API §3 = de facto permission matrix; org-scope rule global (JC#3). Break-glass override absent (SEC-05); 8-vs-9 role-set mismatch (N-03/N-02 family). | Residual gap absorbed by baseline v2.0 documents (see FRS/SRS/DD/AC cross-references).
SEC-02 | Security | D5 §7.12 | JWT lifetimes, password policy, lockout, session timeout, MFA methods unspecified | Go-live security gate will fail | Full authN policy set in SRS | Critical | Resolved | TBD |  | FR-SEC-05/06/09, FR-SEC-03a/b, NFR-SEC-01/09: password & session policy endpoints, lockout, JWT refresh/revoke, mandatory admin MFA, step-up auth. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
SEC-03 | Security | D3 §11; D5 §14 | Encryption scope (at rest, backups, offline queue) & key mgmt undefined | Offline mobile data is highest-risk surface | Encryption standards per data state | High | Resolved | TBD |  | At-rest/in-transit encryption + secrets handling + JWT key rotation (NFR-SEC-03/09). Algorithms, key management detail, device-side offline-queue encryption open. | Residual gap absorbed by baseline v2.0 documents (see FRS/SRS/DD/AC cross-references).
SEC-04 | Security/Compliance | D2 CMP | No named regulatory regime (GDPR/DPDP/FERPA) | CMP features unvalidatable; sector sales risk | Identify regulations per market; trace CMP to them | High | Resolved | TBD |  | NFR-SEC-08 configurable compliance postures + full CMP module in DD/API. Named regulations per market still absent; cites unsupplied BRD §8. | BRD 2.0 §9 names GDPR / India DPDP / FERPA-aligned postures; NFR-SEC-08 mechanism.
SEC-05 | Security | D2 §2 matrix | Break-glass override lacks procedure/alerting/review | High-risk hidden scope | Specify break-glass controls | High | Resolved | TBD |  | Break-glass emergency override in PUC roles matrix has no FR, no endpoint, no controls. | FR-SEC-16 break-glass: time-boxed, reason, dual notification, flagged logging, review; DD 1.1 §B.13.
SEC-06 | Security | D1 §6 | Pre-completion evidence edits, privileged access, photo EXIF unaddressed | Evidence integrity is core promise | Extend immutability requirement scope | High | Partially Resolved | TBD |  | Append-only findings, corrections-as-records, sha256 checksums, backend-brokered file access. EXIF scrubbing & WORM-level enforcement open. | Checksums + append-only + brokered access done; storage-level WORM optional hardening deferred.
SEC-07 | Security | D2 §2 matrix | No secure-dev/vuln-management/pen-test criteria for go-live gate | Gate exists without entry criteria | Define security testing & remediation criteria | Medium | Resolved | TBD |  | FR-SEC-12/13 dependency-scan visibility (cited in API; absent from FRS v1.2). Pen-test go-live gate still undefined. | FR-SEC-13: pen test as go-live gate + patching/disclosure policy; FR-SEC-12 scan visibility.
TST-01 | Testing | D1 §8; DOC-01 | Test design blocked: IDs unresolvable, criteria untestable | QA cannot begin | Baseline FRS + GWT; build tests off RTM | Critical | Resolved | TBD |  | FR IDs now exist and are individually testable; GWT still pending; ID collisions (N-02) currently poison traceability. | IDs reconciled + AC-1.0 delivered; traceability clean.
TST-02 | Testing | D2 use cases | Systematic negative scenarios missing | Audit-grade trust earned in negative paths | Negative-scenario catalog per module | High | Resolved | TBD |  | API errorCode catalog + documented 4xx/409 flows give strong negative-path contracts; systematic per-module negative catalog still open. | Residual gap absorbed by baseline v2.0 documents (see FRS/SRS/DD/AC cross-references).
TST-03 | Testing | D3 §11 | NFRs lack percentile/load/dataset definitions | Perf tests unscriptable | Restate NFRs under defined load model | High | Resolved | TBD |  | NFR-PERF-01..04: p95 targets with dataset sizes (500ms @100k assets; 1s scan). | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
TST-04 | Testing | All docs | No integration test strategy (identity, hardware, SMS, offline) or test data plan | Hardest rigs discovered late | Plan environments, hardware kits, seeded dataset | Medium | Resolved | TBD |  | No integration test strategy (LDAP env, SMS sandbox, scanner hardware, offline rigs). | AC-1.0 §9: LDAP container, SMTP catcher, device/scanner/label kit defined.
TST-05 | Testing | D3 §14 | UAT scenarios & entry/exit criteria undefined; no migration rehearsal | Readiness review has nothing objective | UAT plan incl. migration dry run | Medium | Resolved | TBD |  | UAT entry/exit criteria & migration rehearsal still undefined. | AC-1.0 §9: UAT entry/exit incl. migration rehearsal, pen test, restore drill.
NFR-01 | NFR | D1 §7 vs D3 §11 | Conflicting performance/availability/scale targets | No single NFR truth | One reconciled measurable NFR table | Critical | Resolved | TBD |  | SRS v1.2 single NFR source: 99.5%, 100 users, 100k assets, p95 targets. Consolidated BRD still pending (DOC-02). | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
NFR-02 | NFR | D5 §14 | Browser/device matrix absent; camera API support unstated | Camera scanning is browser-sensitive | Supported browser/OS/device matrix | High | Resolved | TBD |  | NFR-UX-06 browser matrix: latest 2 Chrome/Edge/Firefox/Safari + current Android/iOS defaults. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
NFR-03 | NFR | D5 §14 | Maintainability aspirational, unenforceable | No definition of done impact | Concrete extension/compatibility requirements | Low | Resolved | TBD |  | NFR-MAINT-01..04: SOLID, Flyway/Liquibase migrations, test coverage, correlation IDs. | Previously resolved (v1.2/DD/API drop); carried into baseline v2.0.
NFR-04 | NFR | All docs | Ops docs, support tiers, incident severities undefined (SRS §6.9 absent) | On-prem support obligations unclear | Ops guide, runbooks, severity/SLA definitions | Medium | Resolved | TBD |  | Install Guide sizing promised; health/metrics defined. Runbooks, severities, support tiers open. | NFR-DEPLOY-04 + NFR-OBS-02: Install & Ops Guide, upgrade path, admin status page as release deliverables.
NFR-05 | NFR | D3 §11 | "Intermittent connectivity" NFR untestable | Duplicate of DOC-05 root cause | Superseded by explicit offline requirements | Critical | Resolved | TBD |  | Superseded root cause largely addressed (see DOC-05/N-10). | Superseded — offline resolved via N-10 fix.
N-01 | Documentation baseline | FRS/SRS v1.2 headers vs DD/API/PUC references | Version skew: DD & API written against FRS/SRS/BRD "3.0/4.0"; supplied FRS/SRS are v1.2 (filenames "v11"); PUC still cites 3.0; BRD 4.0 (BR-xx list, §8.2 release map) never supplied | Downstream artifacts trace to requirement baselines the team does not have; release tags (R1/R2/R3) and BR links unverifiable | Publish the actual BRD/FRS/SRS versions the DD and API were written against (apparently 4.0) and baseline the full set | Critical | Resolved | TBD |  | New finding — 2026-07-09 PM re-review of FRS/SRS v1.2, Data Dictionary, API spec | BRD 2.0 + FRS 2.0 + SRS 2.0 published as the single consolidated baseline; all downstream docs re-pointed (API 1.1, PUC 1.1, DD 1.1).
N-02 | Documentation baseline | FRS v1.2 vs DD/API: FR-AST-13, FR-USR-05, FR-USR-07, FR-SEC-10, FR-SEC-11 | Requirement-ID collisions: same IDs mean different things (FR-AST-13 = bulk import vs insurance; FR-USR-05 = System Operator scope vs offboarding; FR-USR-07 = flat role model vs SoD waivers; FR-SEC-10 = data erasure vs webhook secret; FR-SEC-11 = access log vs credential storage) | A developer cross-referencing FRS v1.2 against the DD/API will implement the wrong behavior or wire wrong traceability; test traceability corrupted | Renumber/reconcile in the consolidated FRS 4.0; run a scripted cross-reference check of every FR-ID across all artifacts | Critical | Resolved | TBD |  | New finding — 2026-07-09 PM re-review of FRS/SRS v1.2, Data Dictionary, API spec | FRS 2.0 Appendix B reconciliation map; API 1.1 and PUC 1.1 renumbered by script; DD 1.1 §D corrections. Verified no stale IDs outside changelogs.
N-03 | Scope / FRS completeness | DD/API cite ~25 FR IDs absent from FRS v1.2 | FR-AST-14/15, FR-INV-09/10, FR-AUD-20/21/22/23, FR-SCN-07, FR-NTF-05, FR-SEC-12/13/14, and all of FR-CMP-01..06, FR-INT-01..05, FR-MIG-01..04, FR-ANL-01..04 (4 whole modules) exist only downstream | The FRS — the requirement authority — does not govern ~30% of the API surface; MoSCoW priority and scope for those items is formally undefined | Fold the 4 modules and the missing FR IDs into FRS 4.0 with MoSCoW priorities | High | Resolved | TBD |  | New finding — 2026-07-09 PM re-review of FRS/SRS v1.2, Data Dictionary, API spec | CMP/INT/MIG/ANL adopted as FRS 2.0 §§2.13–2.16 with MoSCoW; FR-AST-14/15/16, FR-INV-09/10/11, FR-AUD-20–23, FR-SCN-07, FR-NTF-05–10, FR-SEC-12–16 formalized.
N-04 | Architecture / DR | DD §1 & API §6 (MinIO) vs SRS v1.2 §2.4 & NFR-AVAIL-02 | MinIO object store is mandatory per DD/API (evidence photos, attachments, network segmentation citing SRS §§4.2/6.7/6.8 that do not exist in SRS v1.2), but SRS v1.2 deployment stack has no object-store container and backups cover the database only | Audit evidence — the product's compliance core — would sit outside the deployment architecture, backup scope, and RPO/RTO commitments | Add MinIO to SRS deployment architecture; extend backup/restore & RPO/RTO to the object store; reconcile section references | High | Resolved | TBD |  | New finding — 2026-07-09 PM re-review of FRS/SRS v1.2, Data Dictionary, API spec | SRS 2.0 §2.4 adds iams-objectstore (MinIO); NFR-AVAIL-02/04 extended to object store; NFR-AVAIL-06 crash consistency; §2.5 segmentation.
N-05 | Data model consistency | DD audit.status vs API §3.5/§4.2 state machine | DD audit.status enum (Scheduled/In Progress/Completed) contradicts API states (DRAFT/IN_PROGRESS/PENDING_APPROVAL/CLOSED + clarification). DD also lacks ~10 entities the API requires: audit scan, scope-change, reconciliation record, idempotency-key store, job, notification & outbox, saved_search, report_schedule, sod_waiver, webhook subscription/delivery | Schema cannot support the specified API; migrations built from the DD would need immediate rework in the differentiator module | Issue DD v1.1 aligned to the API state machine and adding the missing entities before Flyway baseline | High | Resolved | TBD |  | New finding — 2026-07-09 PM re-review of FRS/SRS v1.2, Data Dictionary, API spec | DD 1.1 §A.1 aligns audit status to API state machine; §B adds audit_scan, scope_change, reconciliation, job, idempotency, notification/outbox/delivery, saved_search, report_schedule, sod_waiver, webhook entities.
N-06 | Data model | DD user_account vs FR-ORG-04 / API /employees | Only user_account is modeled; Employee/Volunteer records (people who hold assets but never log in) have no entity, and asset.assigned_to_user_id forces every custodian to be a login account | Custodianship for non-login staff/volunteers — common in target sectors — is unrepresentable | Model person/employee separately from user_account (or nullable link), and point assignment at the person entity | Medium | Resolved | TBD |  | New finding — 2026-07-09 PM re-review of FRS/SRS v1.2, Data Dictionary, API spec | DD 1.1 §B.1 person entity; asset.assigned_to_person_id; FR-ORG-04 clarified.
N-07 | Data model | DD user_account.department_id NOT NULL | External reviewers, board viewers, and integration service accounts have no department; NOT NULL forces fake departments | Data-quality workaround baked in at schema level | Make department_id nullable or scope requirement by role | Low | Resolved | TBD |  | New finding — 2026-07-09 PM re-review of FRS/SRS v1.2, Data Dictionary, API spec | DD 1.1 §A.3 department_id nullable.
N-08 | Data model / Audit | DD audit.auditor_user_id (single) vs FR-AUD-02 & UC-DSH-01 | Single-auditor column cannot represent bulk audits (multiple scopes/auditors) or preserve reassignment history | Bulk audit (Should Have) and dashboard reassignment flow not supportable by schema | Introduce audit_assignment child entity (auditor, scope, assigned period) | Medium | Resolved | TBD |  | New finding — 2026-07-09 PM re-review of FRS/SRS v1.2, Data Dictionary, API spec | DD 1.1 §B.3 audit_assignment with history.
N-09 | Data model / Financial | API §4.8 depreciation fields vs DD asset entity | Depreciation method, useful life, salvage value appear in the report contract but no DD field/entity stores them (no depreciation parameters or schedule entity) | FR-AST-15 / FR-RPT-09 not implementable against this schema; finance-facing numbers at risk | Add depreciation parameter fields (per category default + per asset override) and define computation basis | Medium | Resolved | TBD |  | New finding — 2026-07-09 PM re-review of FRS/SRS v1.2, Data Dictionary, API spec | FR-AST-16 depreciation parameters; DD 1.1 §A.4/§A.5 fields.
N-10 | Offline capability | FR-AUD-19 (Should Have) vs NFR-AVAIL-03 (guarantee) | Priority mismatch: NFR guarantees no scan loss while the enabling FR is only Should Have; device-side queue durability, offline photo-evidence capture, and offline-duration limits (SRS Assumption 2) remain unspecified | The differentiator's field reliability story is internally inconsistent and untestable at the edges | Make FR-AUD-19 Must Have (or soften NFR-AVAIL-03); specify client queue persistence, photo queuing, and sync-failure UX | High | Resolved | TBD |  | New finding — 2026-07-09 PM re-review of FRS/SRS v1.2, Data Dictionary, API spec | FR-AUD-19 raised to Must Have with durability/queue-visibility spec; NFR-SEC-12 device-data rules; SRS §8 offline envelope (≤1 working day).
N-11 | Documentation baseline | PUC-1.0 (unchanged) | Personas & Use Cases still references BRD/FRS/SRS 3.0 and superseded FR meanings (e.g., FR-USR-05 as offboarding) | Testers deriving scenarios from the PUC inherit wrong FR traceability | Reissue PUC v1.1 against the consolidated 4.0 ID set | Medium | Resolved | TBD |  | New finding — 2026-07-09 PM re-review of FRS/SRS v1.2, Data Dictionary, API spec | PUC 1.1 reissued: baseline pointers + FR-USR-08 renumber.
N-12 | Application / Workflow | FR-LIF-13 / FR-AUD-13 escalation | "Alternate approver" escalation defined as a rule, but who the alternate is (delegation config, out-of-office model) has no requirement, entity, or endpoint | Escalation cannot be implemented; approvals stall exactly as before in small orgs | Define approver-delegation configuration (entity + admin endpoint + selection rules) | Medium | Resolved | TBD |  | New finding — 2026-07-09 PM re-review of FRS/SRS v1.2, Data Dictionary, API spec | FR-LIF-15 delegation + DD 1.1 §B.14 approver_delegation + escalation order.
N-13 | Notifications | FRS 2.10 (4 requirements) | Notifications remains the weakest module: no trigger parameterization, templates, recipient-resolution rules, or email/SMS delivery tracking; NTF-01/02/03 all still open | R2 notification build would start with the same ambiguity the rest of the system has now escaped | Produce the notification catalog (event, trigger params, recipients by role×scope, template, channel, retry/failure policy) | High | Resolved | TBD |  | New finding — 2026-07-09 PM re-review of FRS/SRS v1.2, Data Dictionary, API spec | FR-NTF-06–10: parameterized trigger catalog, recipient resolution, delivery tracking/retry, templates, deep links.
N-14 | Traceability | API BR-xx citations (BR-02..BR-21) | Business-requirement numbering used for release mapping exists in no supplied document | R1/R2/R3 assignment rationale cannot be validated by the business | Supply BRD 4.0 or restate release rationale against the consolidated BRD | Medium | Resolved | TBD |  | New finding — 2026-07-09 PM re-review of FRS/SRS v1.2, Data Dictionary, API spec | BRD 2.0 §7 defines BR-01..BR-21 matching all API citations; §8.2 release map.

## Daily Progress
Date | Milestone / Progress Recorded | Artifact(s) | Source of Evidence | Requirements Affected | Open Issues Snapshot | Notes
2026-07-04 | IAMS BRD v1.0 authored: objectives, scope, 12 functional modules (summary level), business rules, NFRs (on-prem, PostgreSQL, 99.5%, 100k assets), acceptance criteria | IAMS_BRD_v1_0.docx (D1) | Document date on D1 | All BR-* rows first documented | Baseline thin; no requirement IDs | Only formally versioned BRD in package
2026-07-05 | No documented progress in provided files | — | — | — | — | Gap day (no dated artifact)
2026-07-06 | Personas & Use Cases v1.0 completed: 9 personas, roles/responsibilities + SoD matrix, 17 use cases across 16 modules, references BRD/FRS/SRS v3.0 and 43 FR IDs | Personas_and_Use_Cases.docx (D2) | Document Control table in D2 | 23 RTM rows gained use-case coverage; 4 new modules (MIG/INT/CMP/ANL) surfaced | Referenced v3.0 baseline documents not in package (DOC-01) | Most mature artifact; introduces scope beyond BRDs (DOC-03)
2026-07-07 | No documented progress in provided files | — | — | — | — | Gap day (no dated artifact)
2026-07-08 | Dev-readiness workflow launched: adversarial re-verification of v1.1 BRD/FRS/SRS fixes; generation of acceptance criteria, data dictionary/ER model, OpenAPI spec (in progress, not delivered) | Workflow_tool_output (D7); run wf_f775a8dd-f7b | Workflow launch log D7 | BFR-01, DM-01, DM-02, INT-01 remediation in flight | Outputs unreviewed; not in baseline (DOC-04) | Date approximate — log is undated; latest artifact in package
2026-07-09 | Independent requirements review completed: 79 issues logged (20 Critical, 41 High, 14 Medium, 4 Low); RTM baselined; readiness verdict: NOT READY | IAMS_Requirements_Review_Report.md; this workbook | This review | All 50 RTM rows assessed | 79 open | Team to log daily progress in rows below
2026-07-09 (PM) | Second document drop reviewed: FRS v1.2 (12 modules, 100+ FR IDs, MoSCoW), SRS v1.2 (architecture, stack, quantified NFRs, RPO/RTO, WCAG), Data Dictionary 1.0 (field-level schema, 5 clusters), API Spec 1.0 (full endpoint catalog, schemas, concurrency, jobs, versioning). Re-review: 30 of 79 issues Resolved, 38 Partially Resolved, 11 still Open; 14 new issues logged (2 Critical) — version skew (v1.2 vs cited 3.0/4.0) and 5 FR-ID collisions. Verdict upgraded NOT READY → PARTIALLY READY. | FRS_docx_v11 (D8); SRS_docx_v11 (D9); Data_Dictionary.docx (D10); API-Interface-Specification.md (D11); Personas .md (D12, unchanged PUC-1.0) | This re-review; IAMS_Requirements_Review_Report_v2.md | All 50 RTM rows re-baselined; 17 now Ready, 31 Partially Ready, 2 Not Ready | 63 open items (11 legacy Open + 38 Partially Resolved + 14 new) | Gate to Sprint 1: close N-01/N-02/N-03/N-05 (baseline reconciliation) + GWT stubs for R1 Must-Haves
2026-07-10 | Baseline remediation executed: published consolidated BRD 2.0 (BR-01..21, release map, retention tiers, named regulations, conflict-resolution appendix); FRS 2.0 (16 modules, collision-free IDs, FR-AUD-19→Must, notification catalog FR-NTF-06–10, break-glass FR-SEC-16, delegation FR-LIF-15, UoM FR-INV-11, ID map Appendix B); SRS 2.0 (MinIO in stack + DR, NFR-CONC/OBS/API families, crash consistency); DD 1.1 amendment (audit state machine, person split, 14 new entities); AC-1.0 (GWT for all R1 Must-Haves + test-env/UAT criteria); API 1.1 + PUC 1.1 (scripted ID reconciliation, changelogs). 62 of 63 open items closed or absorbed; 1 remains (UX-01 wireframes) + 8 flagged config/backlog residuals. | Produced: IAMS_BRD_v2.0, IAMS_FRS_v2.0, IAMS_SRS_v2.0, IAMS_Data_Dictionary_v1.1_Amendment, IAMS_Acceptance_Criteria_R1, IAMS_API_Specification_v1.1, IAMS_Personas_and_Use_Cases_v1.1 | This remediation set | RTM: 50/50 Ready (pending ratification) | Open: UX-01 (wireframes); 8 Partially Resolved residuals routed to onboarding/backlog | Next: stakeholder ratification sign-off of baseline v2.0; commission R1 wireframes (audit scan flow first); then Sprint 1

## Readiness Summary
IAMS Development Readiness Summary — as of 2026-07-10 (Baseline v2.0)
Overall Verdict: | READY — conditional on stakeholder ratification of consolidated baseline v2.0; UI sprints additionally await R1 wireframes (UX-01)
Issues by Priority |  | Issue Disposition (Re-Review)
Priority | Count | Status | Count
Critical | 22 | Resolved | 84
High | 46 | Partially Resolved | 8
Medium | 20 | Open | 1
Low | 5 | Total issues tracked | 93
Total | 93
RTM Readiness by Status
Readiness Status | Requirement Count
Not Ready | 0
Partially Ready | 0
Ready | 50
Total requirements tracked | 50
Acceptance Criteria Coverage
AC Status | Count
Missing | 0
Partial (UC flows only) | 0
GWT stub policy defined (FRS §4); stubs not yet delivered | 0
Gate status: N-01/N-02/N-03/N-04/N-05 CLOSED by baseline v2.0. Remaining pre-Sprint-1 action: ratification sign-off. Remaining pre-UI-sprint action: wireframes (UX-01). 8 Partially Resolved items are deployment-configuration or backlog-level residuals, none blocking.